## Slide 1
Project Background
Analysis I: Prefab Exterior
Analysis II: Precast Footing
Analysis III: Modularization
Analysis IV: Sustainability
Conclusions
Closing Remarks
Jessica Serna
Construction Option
Advisor: Dr. Obonyo
Doylestown Hospital
Heart Institute

## Slide 2
Project Background
Analysis I: Prefab Exterior
Analysis II: Precast Footing
Analysis III: Modularization
Analysis IV: Sustainability
Conclusions
Closing Remarks
PRESENTATION OVERVIEW
ANALYSIS I PREFAB EXTERIOR WALL
ANALYSIS II PRECAST FOOTINGS
ANALYSIS III MODULAR BATHROOM PODS
ANALYSIS IV SUSTAINABILITY

## Slide 3
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Phase D: Heart Institute
595 W State Street, Doylestown, PA
66,837 SF
$40M
March 2017 - November 2019
Project Name:
Location:
Size:
Cost:
Schedule:
Doylestown Hospital Heart Institute
PROJECT INFORMATION
DD
Project Breaks Ground
Substantial Completion
Final Completion
February 2019
November 2019
March 2017
September 2017
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 4
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
SITE LOGISTICS
Design-Bid-Build
Doylestown Health
Joint Venture
Delivery Method:
Owner:
GC’s:
Norwood Company – John S. McManus Inc
PROJECT INFORMATION
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 5
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS I: PREFAB EXTERIOR WALL PANELS
Problem: Limited Laydown Area on Site Active Loading Dock
Schedule Delays Early On
Goals: Reduce Site Congestion
Reduce Schedule Duration
Improve Quality
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 6
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
CURRENT SYSTEM
ANALYSIS I: PREFAB EXTERIOR WALL PANELS
PROPOSED SYSTEM
Panels Manufactured Off-site
High quality
Lightweight
Installed with Crane
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 7
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS I: PREFAB EXTERIOR WALL PANELS
100 Ton Crane
Begin on Northwest side
Counterclockwise
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 8
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS I: PREFAB EXTERIOR WALL PANELS
May 15, 2018
Aug 14, 2018
May 15, 2018
June 15, 2018
41 Day
Schedule Reduction
20,307 SF of Prefab
Average Panel 198 SF
103 Panels in Total
PREFAB SCHEDULE − 23 DAYS
CURRENT SCHEDULE− 64 DAYS
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 9
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS I: PREFAB EXTERIOR WALL PANELS
COST COMPARISON
PREFAB WALL
$12.09 PER SF
+ $245,512 TOTAL PROJECT COST
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 10
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS I: PREFAB EXTERIOR WALL PANELS
CONCLUSION/RECOMMENDATION
PREFAB WALL: RECOMMENDED
Accelerates Schedule
Reduces Labor
Improves Quality
Less Site Laydown Required
Increases Project Cost
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 11
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS II: PRECAST FOOTINGS
Problem: Behind Schedule Due to Delays with Underground Utilities
Goals: Reduce Foundation Schedule Duration
Improve Quality
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 12
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS II: PRECAST FOOTINGS
CURRENT METHOD
Analysis III: Modularization
Cast-in Place
Sloped Site - Footings on Ground Floor and First Floor
41 Footings
Size: 3x3 - 11x11
Analysis I: Prefab Exterior
Analysis II: Precast Footing
Ground Floor
First Floor
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 13
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS II: PRECAST FOOTINGS
LIMITATIONS
Analysis III: Modularization
Truck Width: 8’6”
Load: 80,000 lbs
25 Oversized Footings
Additional Fees
Analysis I: Prefab Exterior
Analysis II: Precast Footing
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 14
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS II: PRECAST FOOTINGS
SCHEDULE COMPARISON
Analysis III: Modularization
Analysis I: Prefab Exterior
Analysis II: Precast Footing
Ground Floor
10 Days
First Floor
5 Days
Interior
5 Days
Atrium
5 Days
Precast Footings
14 Days
11 Day Reduction
Current Schedule
Precast Schedule
COST COMPARISON
Oversized Truck
Additional Equipment
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 15
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS II: PRECAST FOOTINGS
Analysis III: Modularization
Analysis I: Prefab Exterior
Analysis II: Precast Footing
CONCLUSION/RECOMMENDATION
PRECAST FOOTINGS: NOT RECOMMENDED
Accelerates Schedule – 11 Days
Reduces Material On Site
Increases Project Cost
Additional Site Equipment
Notes: Footings vary in size
Only 2 footings per truck delivery

## Slide 16
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS III: MODULARIZATION
PATIENT BATHROOMS
Problem: Project Over Budget
Tight Schedule
Goals: Reduce Schedule Duration
Reduce Cost
Improve Quality
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 17
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS III: MODULAR BATHROOM
Analysis I: Prefab Exterior
TYPICAL PATIENT BATHROOM
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 18
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS III: MODULAR BATHROOM
Analysis I: Prefab Exterior
TYPICAL PATIENT BATHROOM
Analysis II: Precast Footing
Analysis III: Modularization
Redundancy: Identical Second and Third Floors
48 Bathrooms
10’3” x 6’
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 19
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS III: MODULAR BATHROOM
Analysis I: Prefab Exterior
COST COMPARISON
Analysis II: Precast Footing
Analysis III: Modularization
Transportation
6 pods per truck
+$505/delivery
Total Inc. $4032
Labor
Reduced Labor Hours
Total Dec. $26,880
SCHEDULE COMPARISON
Total Duration: 4 Days
Original Duration: 36 Days
32 Day Reduction
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 20
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS III: MODULAR BATHROOM
Analysis I: Prefab Exterior
ELECTRICAL BREADTH
Analysis II: Precast Footing
Analysis III: Modularization
MC CABLE ON CABLE TRAYS
Electrical Breadth
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 21
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS III: MODULAR BATHROOM
Analysis I: Prefab Exterior
CURRENT METHOD
Analysis II: Precast Footing
Analysis III: Modularization
Electrical Breadth
¾” EMT Conduit
600V
CABLE TRAYS
No limit on number of conductors
Trade size AWG 12/2 - 12/4
600 Maximum voltage rating
THHN conductor insulation
2 means of grounding
Meet UL and National Electrical Code (NEC) ratings
CABLE TRAYS
Support insulated electrical cables such as MC Cables that are used for power distribution, control, and communication
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 22
Project Background
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS III: MODULAR BATHROOM
Analysis I: Prefab Exterior
CONCLUSION/RECOMMENDATION
MODULAR BATHROOM PODS
Accelerates Schedule – 32 Days
Reduces Material On Site
Labor Cost Savings
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Footings vary in size
Only 2 footings per truck delivery

## Slide 23
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS IV: STUDENT LEADERSHIP IN SUSTAINABILITY
PACE INDUSTRY TOPIC
Problem: Lack Incorporation of Sustainable Design
Goals: Reduce Foundation Schedule Duration
Improve Quality
Analysis II: Precast Footing
Analysis III: Modularization
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 24
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS IV: SUSTAINABILITY
Analysis II: Precast Footing
Analysis III: Modularization
RESEARCH
The University of British Columbia - Centre for Interactive Research on Sustainability
Surveys & Interviews
Yestermorrow-UMass Semester in Sustainable Design/Build
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 25
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS IV: SUSTAINABILITY
Analysis II: Precast Footing
Analysis III: Modularization
FINDINGS
10 AE students/Alumni Interviewed – 3rd Year to 2 Years in the Industry
100% Interested in Sustainable Building Design
1/10 Felt comfortable about incorporating sustainability in real world-applications
80% Learned about sustainable design in class
Sustainable Building Materials/Benefits
LEED Certification
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 26
Project Background
Analysis I: Prefab Exterior
Analysis IV: Sustainability
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
ANALYSIS IV: SUSTAINABILITY
Analysis II: Precast Footing
Analysis III: Modularization
CONCLUSION/RECOMMENDATION
Guest Speakers
More Incorporation in 300 Level AE Classes
Include Sustainable Design in each Course
Study Abroad Opportunities
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 27
Project Background
Analysis I: Prefab Exterior
Conclusions
Closing Remarks
Doylestown Hospital Heart Institute
CONCLUSIONS
Analysis II: Precast Footing
Analysis III: Modularization
Analysis IV: Sustainability
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 28
Project Background
Analysis I: Prefab Exterior
Closing Remarks
Doylestown Hospital Heart Institute
CLOSING REMARKS
Analysis II: Precast Footing
Analysis III: Modularization
Analysis IV: Sustainability
Conclusions
SPECIAL THANKS
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing

## Slide 29
Project Background
Analysis I: Prefab Exterior
Closing Remarks
Doylestown Hospital Heart Institute
CLOSING REMARKS
Analysis II: Precast Footing
Analysis III: Modularization
Analysis IV: Sustainability
Conclusions
QUESTIONS?
Notes: Addition to an existing hospital, 4 levels
Joint Occupancy/active hospital
Encompasses existing